# Project Charter

# Purpose

Consolidate the three regional TAMS (Travel Assistance Management System) instances into a single Salesforce-based platform that serves patients seeking subsidised medical travel, the practitioners who deliver assessments, and PTSF's regional operations teams.

# Business drivers

Retire legacy TAMS — three fragmented regional stacks with divergent data models and no unified reporting.

Patient experience — self-service application intake, real-time status, localised communication.

PHI compliance — enforce Private OWD on medical history, restriction rules, break-glass audit trail.

Operational visibility — regional dashboards for Team Managers and executives.

# Scope

## In scope (20 delivered intents)

Salesforce org provisioning + DevOps pipeline (INT-001)

Identity + regional user model (INT-002, INT-005)

Patient + Practitioner login surfaces (INT-003)

PHI security foundation + region scoping (INT-004, INT-020)

Patient portal onboarding wizard (INT-006)

Async HIC integration (INT-007)

Application lifecycle with auto-reject (INT-008)

Practitioner community + auto-assignment (INT-009)

SLA reassignment (INT-010)

Digital assessment form (INT-011)

15-day escalation (INT-012)

Assessor Service Console (INT-013)

Subsidy determination Flow (INT-014)

Chat + bot + KB (INT-015)

Reporting (INT-016)

Practitioner MHE temporary access (INT-019)

TAMS→Salesforce migration ETL (INT-017)

Per-region cutover with dual-run (INT-018)

## Out of scope

Real HIC vendor endpoint enablement (deferred to production)

Real IdP metadata configuration (deferred to PTSF IT handoff)

TAMS hardware decommission (PTSF IT owns)

Global AD federation

Patient-facing analytics

Practitioner acceptance rate roll-up

# Success criteria

All 20 intents ✅ Delivered (met — 2026-09-30)

Automated test coverage ≥ 39 Apex tests green (met)

Zero critical defects on merge to develop (met)

Structural org-probes verified for all ✅ criteria (met — verify-evidence 2026-09-30)

15 pending 👁 manual sign-offs completed before production cutover (pending)

Regional cutover with < 4 hours per-region downtime (pending)

# Governance

Trusted Guide (Architect of record): Prashant Kumar. Owns Intent, signs off ratification, decides scope disputes.

Delivery method: QL AI-native (agent builds; human ratifies). Every scope change carries a decisions/ record. intents/ is canonical; scopezilla/ is a read-only mirror.

Pipeline: feature/ → develop → release/ → main → prod. Agent lane ends at PR into develop.

CI gates: validate, drift, coverage --gate — no --no-verify, no bypass.

Reviews: intent-only PRs skip build gauntlet but still run Intent trust chain; build PRs run the full CI.

# Assumptions

See delivery/raid-log.md § Assumptions.

# Risks

Top risks: HIC vendor spec still open, IdP metadata not received, 15 manual sign-offs pending, TAMS cutover dual-run drift. See delivery/raid-log.md § Risks.

# High-level timeline

| Phase | Focus | Status |
| --- | --- | --- |
| 0 | Discovery + scope | Complete |
| 1 | Foundation (org, identity, security) | ✅ Delivered |
| 2 | Patient intake + HIC | ✅ Delivered |
| 3 | Practitioner + assessment | ✅ Delivered |
| 4 | Business logic + operational surfaces | ✅ Delivered |
| 5 | Migration + cutover | ✅ Delivered (metadata); cutover pending |

# Deliverables (top-level)

Working org — epic.out.e68d765f4115@orgfarm.salesforce.com (203 components deployed)

20 intent packages — each with intent.md, design.md, test-script.md, runbook

Test artifacts — 39 Apex tests, seed data script, manual test checklist

Governance artifacts — intent ledger, decision records, RAID log, RACI matrix, this charter

Capability map — delivery/capability-map.html for stakeholder walkthroughs