# Status Report

# Executive summary

Overall status: GREEN. All 20 planned intents delivered; metadata deployed to sandbox; automated test coverage green (39/39); 15 delivered intents carry 👁 manual sign-offs pending human validation (surfaced, not gated). Two build defects surfaced and fixed this cycle; one governed scope refinement (INT-008) recorded.

# Delivery metrics

| Metric | Value |
| --- | --- |
| Intents delivered | 20 / 20 |
| Metadata components deployed | 203 |
| Apex test pass rate | 39 / 39 (100%) |
| Org-probe assertions verified | All ✅ criteria — evidence under intents/INT-NNN/verify-evidence/ |
| Manual sign-offs complete | 0 / 30 pending criteria (5 delivered intents fully signed via CI + auto-cover) |
| Decision records | 24 (last: 2026-09-30, INT-008 lock scope narrowed) |
| CI gate status | Green — validate, drift, coverage all pass |

# Delivered this cycle

Bug fix — HIC platform event required-field regression (2c892b6)

Governed refinement — INT-008 Locked_After_Submission scope narrowed to unblock INT-010 SLA reassignment (ebad0ca)

Org-probe verification — INT-007 (Named Credential), INT-010 (Assignment SLA Flow), INT-011 (Assessment__c object) all green in the sandbox

Test-script proof_hash regen across 9 drifted intents

5 unpointed 📋 accepted-gap rows converted to properly-parseable pointed gaps

Seed data loaded — 6 test Contacts, 5 Subsidy Applications, 1 Assignment

Tester walkthrough — delivery/test-plan.md + Word checklist delivery/PTSF-Manual-Tests.docx

Governance docs — Project Charter, RAID Log, RACI Matrix

# Milestones

| Milestone | Target | Status |
| --- | --- | --- |
| Phase 1 (Foundation) deployed | — | ✅ Done |
| Phase 2 (Patient + HIC) deployed | — | ✅ Done |
| Phase 3 (Practitioner) deployed | — | ✅ Done |
| Phase 4 (Business logic) deployed | — | ✅ Done |
| Phase 5 (Migration) deployed | — | ✅ Done |
| Manual test sign-offs complete | Cutover -14d | 🟡 Pending |
| IdP metadata received (INT-002) | Cutover -21d | 🔴 Not received |
| Facebook Dev App configured (INT-003) | Cutover -14d | 🔴 Not started |
| HIC vendor endpoint enablement | Cutover -7d | 🔴 Blocked on Q-007-1 |
| AMER pilot cutover weekend | TBD | 🔴 Not scheduled |
| EMEA cutover | AMER + 4 weeks | 🔴 Not scheduled |
| APAC cutover | EMEA + 4 weeks | 🔴 Not scheduled |

# Risks (top 3)

See delivery/raid-log.md for the full list.

HIC vendor payload spec open (Q-007-1) — HIGH impact; mocked tests prove mechanism but not the real contract. Mitigation: Named Credential + placeholder endpoint deployed; retry logic proven; enablement is a runbook step.

IdP metadata not received — HIGH impact on INT-002 acceptance; JIT handler is built and ready. Mitigation: escalate to PTSF IT for regional AD metadata + certificates.

30 manual sign-offs pending — MEDIUM impact; tester walkthrough + Word checklist ready. Mitigation: 15 items are doable now in the sandbox; the rest are blocked on persona provisioning / external systems.

# Next steps

Trusted Guide + Salesforce Admin work Section A of PTSF-Manual-Tests.docx (15 items, ~1 day)

PTSF IT: provide EMEA/AMER/APAC AD IdP metadata + certs

PTSF Marketing: create Facebook Dev App + share credentials

HIC vendor: confirm payload spec (Q-007-1) — unblock INT-007-C9

Schedule AMER pilot cutover weekend once external blockers clear

# Blockers

PTSF IT to provide IdP metadata (INT-002, INT-005)

PTSF Marketing to provide Facebook Dev App (INT-003)

HIC vendor payload spec (INT-007)

Cutover weekend calendar (INT-018)

# Team

| Role | Person |
| --- | --- |
| Trusted Guide / Architect of record | Prashant Kumar |
| AI builder | Claude Opus 4.7 (1M context) |
| Target org | ptsf-lab sandbox (epic.out.e68d765f4115@orgfarm.salesforce.com) |
| Repo | https://github.com/kumarprashant-byte/AI-Cohort-PTSF-Labs |